## Gantt chart
not started
in progress
completed
delay
Latin American-European network on waste electrical and electronic equipment research, development and analyses" (LaWEEEda)
| Project Coordination: | BOKU |  | Version: | 1.0
| Project start | 2016-10-15 |  | Status: | Beginning
| Today | 2017-05-09 | [7 empty] | PM 1 | [27 empty] | CW 45 | [6 empty] | CW 46 | [6 empty] | CW 47 | [6 empty] | CW 48 | [6 empty] | CW 49 | [6 empty] | CW 50 | [6 empty] | CW 51 | [6 empty] | CW 52 | [6 empty] | CW 1 | [6 empty] | CW 2 | [6 empty] | CW 3 | [6 empty] | CW 4 | [6 empty] | CW 5 | [6 empty] | CW 6 | [6 empty] | CW 7 | [6 empty] | CW 8 | [6 empty] | CW 9 | [6 empty] | CW 10 | [6 empty] | CW 11 | [6 empty] | CW 12 | [6 empty] | CW 13 | [6 empty] | CW 14 | [6 empty] | CW 15 | [6 empty] | CW 16 | [6 empty] | CW 17 | [6 empty] | CW 18 | [6 empty] | CW 19 | [6 empty] | CW 20 | [6 empty] | CW 21 | [6 empty] | CW 22 | [6 empty] | CW 23 | [6 empty] | CW 24 | [6 empty] | CW 25 | [6 empty] | CW 26 | [6 empty] | CW 27 | [6 empty] | CW 28 | [6 empty] | CW 29 | [6 empty] | CW 30 | [6 empty] | CW 31 | [6 empty] | CW 32 | [6 empty] | CW 33 | [6 empty] | CW 34 | [6 empty] | CW 35 | [6 empty] | CW 36 | [6 empty] | CW 37 | [6 empty] | CW 38 | [6 empty] | CW 39 | [6 empty] | CW 40 | [6 empty] | CW 41 | [6 empty] | CW 42 | [6 empty] | CW 43 | [6 empty] | CW 44 | [6 empty] | CW 45 | [6 empty] | CW 46 | [6 empty] | CW 47 | [6 empty] | CW 48 | [6 empty] | CW 49 | [6 empty] | CW 50 | [6 empty] | CW 51 | [6 empty] | CW 52 | [6 empty] | CW 1 | [6 empty] | CW 2 | [6 empty] | CW 3 | [6 empty] | CW 4 | [6 empty] | CW 5 | [6 empty] | CW 6 | [6 empty] | CW 7 | [6 empty] | CW 8
[38 empty] | 2016-11-07 | [6 empty] | 2016-11-14 | [6 empty] | 2016-11-21 | [6 empty] | 2016-11-28 | [6 empty] | 2016-12-05 | [6 empty] | 2016-12-12 | [6 empty] | 2016-12-19 | [6 empty] | 2016-12-26 | [6 empty] | 2017-01-02 | [6 empty] | 2017-01-09 | [6 empty] | 2017-01-16 | [6 empty] | 2017-01-23 | [6 empty] | 2017-01-30 | [6 empty] | 2017-02-06 | [6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29 | [6 empty] | 2017-06-05 | [6 empty] | 2017-06-12 | [6 empty] | 2017-06-19 | [6 empty] | 2017-06-26 | [6 empty] | 2017-07-03 | [6 empty] | 2017-07-10 | [6 empty] | 2017-07-17 | [6 empty] | 2017-07-24 | [6 empty] | 2017-07-31 | [6 empty] | 2017-08-07 | [6 empty] | 2017-08-14 | [6 empty] | 2017-08-21 | [6 empty] | 2017-08-28 | [6 empty] | 2017-09-04 | [6 empty] | 2017-09-11 | [6 empty] | 2017-09-18 | [6 empty] | 2017-09-25 | [6 empty] | 2017-10-02 | [6 empty] | 2017-10-09 | [6 empty] | 2017-10-16 | [6 empty] | 2017-10-23 | [6 empty] | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13 | [6 empty] | 2017-11-20 | [6 empty] | 2017-11-27 | [6 empty] | 2017-12-04 | [6 empty] | 2017-12-11 | [6 empty] | 2017-12-18 | [6 empty] | 2017-12-25 | [6 empty] | 2018-01-01 | [6 empty] | 2018-01-08 | [6 empty] | 2018-01-15 | [6 empty] | 2018-01-22 | [6 empty] | 2018-01-29 | [6 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19
 | time axis 2016-10-10 to 2018-02-25
WP | Task | Responsibility | Start | Duration [days] | End of WP | progress | CalcDone | CalcDate | Status | time axis 2016-10-10 to 2018-02-25
0 | Projekt Coordination | BOKU | 2016-10-15 | 1095 | 2019-10-14 | 19.33% | 212 | 2017-05-14 | in progress
1 | Creating the information basis | TUHH | 2016-10-15 | 212 | 2017-05-14 | 68% | 144 | 2017-03-07 | in progress
1.1 | Compilation of a holistic inventory of existing teaching/training capacities and related gaps and needs | TUHH, all partners | 2016-10-15 | 151 | 2017-03-14 | 85% | 128 | 2017-02-19 | in progress
1.2 | Compilation of established University-Enterprises collaboration approaches and best practise examples (at the participating organisation and in the area of e-waste management) | TUHH, partners | 2016-10-15 | 151 | 2017-03-14 | 80% | 121 | 2017-02-12 | in progress
1.3 | Preparatory activities regarding specific national and regional, social, gender and ethical aspects respecting national and regional specialities | ULSA, all partners from partner countries | 2016-10-15 | 151 | 2017-03-14 | 50% | 76 | 2016-12-29 | in progress
1.4 | Selection of modules, courses and educational products for academic education and CPD | TUHH, all partners | 2017-02-15 | 89 | 2017-05-14 | 75% | 67 | 2017-04-22 | in progress
1.5 | Organisation of preparatory workshops | ULSA | 2016-12-15 | 151 | 2017-05-14 | 50% | 76 | 2017-02-28 | in progress
2 | University-Enterprise Collaboration and Trainings centre | UFRJ | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
2.1 | Planning and development of the LaWEEda University-Enterprise Business and Trainings centres and Network | UFRJ, all other partners | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
2.2 | Develop roadmaps | UFRJ, all other partners | 2017-11-15 | 699 | 2019-10-14 | 0% | 0 | 2017-11-14 | not started
2.3 | Implementation of a web platform to support the centre | BOKU, UFRJ | 2017-11-15 | 638 | 2019-08-14 | 0% | 0 | 2017-11-14 | not started
2.4 | Businessplan development | UFRJ, all other partners | 2018-04-15 | 487 | 2019-08-14 | 0% | 0 | 2018-04-14 | not started
3 | Academic Education | ULSA | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
3.1 | Detailed definition of academic educational products to be adapted and developed | BOKU, all academic partners, input from non-academic partners | 2017-05-15 | 153 | 2017-10-14 | 0% | 0 | 2017-05-14 | not started
3.2 | Adaptation of educational products for Academic Education | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 0% | 0 | 2017-11-14 | not started
3.3 | Development of NEW higher education products | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 0% | 0 | 2017-11-14 | not started
3.4 | Train-the-teacher on new and adapted higher education products | ULSA, all academic partners | 2018-06-15 | 426 | 2019-08-14 | 0% | 0 | 2018-06-14 | not started
3.5 | Piloting and improvement of the developed academic products | ULSA, all academic partners | 2018-08-15 | 365 | 2019-08-14 | 0% | 0 | 2018-08-14 | not started
3.6 | Preparation of approval of new and adapted educational products into existing curricula | ULSA, all academic partners | 2018-12-15 | 243 | 2019-08-14 | 0% | 0 | 2018-12-14 | not started
4 | Continuing professional development (CPD) | BOKU | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
4.1 | Detailed definition of CPD educational products to be adapted and developed | BOKU, all other partners | 2017-05-15 | 153 | 2017-10-14 | 0% | 0 | 2017-05-14 | not started
4.2 | Adaptation of existing educational products for CPD | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 0% | 0 | 2017-05-14 | not started
4.3 | Development of NEW CPD educational products | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 0% | 0 | 2017-05-14 | not started
4.4 | Train-the-trainer on new and adapted CPD educational products | BOKU, all other partners | 2018-06-15 | 426 | 2019-08-14 | 0% | 0 | 2018-06-14 | not started
4.5 | Piloting and improvement of the developed CPD products | BOKU, all other partners | 2018-08-15 | 365 | 2019-08-14 | 0% | 0 | 2018-08-14 | not started
4.6 | Certification of new and adapted educational CPD products | UFRJ, all other partners | 2018-12-15 | 243 | 2019-08-14 | 0% | 0 | 2018-12-14 | not started
5 | Teaching tools and techniques | TUON | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1 | Selection, development and adaptation of state of the art of modern teaching tools and methods | TUON, all University partners | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1.1 | Implementation of e-learning | TUON, all other partners | 2017-05-15 | 335 | 2018-04-14 | 0% | 0 | 2017-05-14 | not started
5.1.2 | Development of a “Digital library” | TUON | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1.3 | Trainings related to entrepreneurial skills | BOKU, all other partners | 2017-08-15 | 426 | 2018-10-14 | 0% | 0 | 2017-08-14 | not started
5.1.4 | Implementation of shared trainings work stations | UFRJ, all other partners | 2017-08-15 | 426 | 2018-10-14 | 0% | 0 | 2017-08-14 | not started
5.2 | Piloting and improvement of new tools | TUON, all partners | 2018-11-15 | 120 | 2019-03-14 | 0% | 0 | 2018-11-14 | not started
5.3 | Prepare Integration of new tools into the University structures as well as at Companies site and in the collaboration centre | UNESP, all other Partners from Brazil and Nicaragua | 2017-11-15 | 577 | 2019-06-14 | 0% | 0 | 2017-11-14 | not started
6 | Project Monitoring and Quality Assurance | TUHH | 2016-10-15 | 1095 | 2019-10-14 | 86.67% | 949 | 2019-05-21 | in progress
6.1 | Development of a Quality Plan/Guidelines and exchange of best practise | TUHH, all partners | 2016-10-15 | 182 | 2017-04-14 | 100% | 182 | 2017-04-14 | in progress
6.2 | Implementation of continuous Quality monitoring | TUHH, all WP Leaders with support of WP contributors | 2017-01-15 | 1003 | 2019-10-14 | 85% | 853 | 2019-05-17 | in progress
6.3 | Coordination of documentation of best practise and lessons learned from trainings development and integration | TUHH, all WP Leaders | 2017-04-15 | 913 | 2019-10-14 | 75% | 685 | 2019-02-28 | in progress
7 | Project Dissemination and Exploitation | UNESP | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.1 | Development of a detailed Dissemination strategy | UNESP, all other partners | 2016-10-15 | 92 | 2017-01-14 | 0% | 0 | 2016-10-14 | not started
7.2 | Development of website and dissemination material | UNESP, all partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.3 | Ongoing engagement of all stakeholder groups and support of consortium partners | UNESP, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.4 | IPR management and Exploitation | BOKU, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
8 | Project Management | BOKU | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
8.1 | Management of the Project start | BOKU, all other partners and associated partners for the Kick-Off meeting | 2016-10-15 | 92 | 2017-01-14 | 0% | 0 | 2016-10-14 | not started
8.2 | Ongoing Project Coordination | BOKU, all other partners and associated partners for the interim Consortium meeting | 2017-02-15 | 972 | 2019-10-14 | 0% | 0 | 2017-02-14 | not started
8.3 | Financial and content controlling | BOKU, WP leaders | 2017-02-15 | 972 | 2019-10-14 | 0% | 0 | 2017-02-14 | not started
8.4 | Management of the Project close down | BOKU, all other partners and associated partners for the final Consortium meeting | 2019-08-15 | 61 | 2019-10-14 | 0% | 0 | 2019-08-14 | not started
Formulas:
CalcDate = [Start]+[CalcDone]-1

## auf PM
Latin American-European network on waste electrical and electronic equipment research, development and analyses" (LaWEEEda)
| Project Coordination: | BOKU |  | Version: | 1.0
| Project start | 2016-10-15 |  | Status: | Beginning
| Today | 2017-05-09
WP | Task | Responsibility | Start | Duration [days] | End of WP | progress | CalcDone | CalcDate | Status | PM 1 | PM 2 | PM 3 | PM 4 | PM 5 | PM 6 | PM 7 | PM 8 | PM 9 | PM 10 | PM 11 | PM 12 | PM 13 | PM 14 | PM 15 | PM 16 | PM 17 | PM 18 | PM 19 | PM 20 | PM 21 | PM 22 | PM 23 | PM 24 | PM 25 | PM 26 | PM 27 | PM 28 | PM 29 | PM 30 | PM 31 | PM 32 | PM 33 | PM 34 | PM 35 | PM 36
0 | Projekt Coordination | BOKU | 2016-10-15 | 1095 | 2019-10-14 | #DIV/0! | #DIV/0! | #DIV/0! | in progress
1 | Creating the information basis | TUHH | 2016-10-15 | 212 | 2017-05-14 | 0% | 0 | 2016-10-14 | not started
1.1 | Compilation of a holistic inventory of existing teaching/training capacities and related gaps and needs | TUHH, all partners | 2016-10-15 | 151 | 2017-03-14 | 0% | 0 | 2016-10-14 | not started
1.2 | Compilation of established University-Enterprises collaboration approaches and best practise examples (at the participating organisation and in the area of e-waste management) | TUHH, partners | 2016-10-15 | 151 | 2017-03-14 | 0% | 0 | 2016-10-14 | not started
1.3 | Preparatory activities regarding specific national and regional, social, gender and ethical aspects respecting national and regional specialities | ULSA, all partners from partner countries | 2016-10-15 | 151 | 2017-03-14 | 0% | 0 | 2016-10-14 | not started
1.4 | Selection of modules, courses and educational products for academic education and CPD | TUHH, all partners | 2017-02-15 | 89 | 2017-05-14 | 0% | 0 | 2017-02-14 | not started
1.5 | Organisation of preparatory workshops | ULSA | 2016-12-15 | 151 | 2017-05-14 | 0% | 0 | 2016-12-14 | not started
2 | University-Enterprise Collaboration and Trainings centre | UFRJ | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
2.1 | Planning and development of the LaWEEda University-Enterprise Business and Trainings centres and Network | UFRJ, all other partners | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
2.2 | Develop roadmaps | UFRJ, all other partners | 2017-11-15 | 699 | 2019-10-14 | 0% | 0 | 2017-11-14 | not started
2.3 | Implementation of a web platform to support the centre | BOKU, UFRJ | 2017-11-15 | 638 | 2019-08-14 | 0% | 0 | 2017-11-14 | not started
2.4 | Businessplan development | UFRJ, all other partners | 2018-04-15 | 487 | 2019-08-14 | 0% | 0 | 2018-04-14 | not started
3 | Academic Education | ULSA | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
3.1 | Detailed definition of academic educational products to be adapted and developed | BOKU, all academic partners, input from non-academic partners | 2017-05-15 | 153 | 2017-10-14 | 0% | 0 | 2017-05-14 | not started
3.2 | Adaptation of educational products for Academic Education | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 0% | 0 | 2017-11-14 | not started
3.3 | Development of NEW higher education products | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 0% | 0 | 2017-11-14 | not started
3.4 | Train-the-teacher on new and adapted higher education products | ULSA, all academic partners | 2018-06-15 | 426 | 2019-08-14 | 0% | 0 | 2018-06-14 | not started
3.5 | Piloting and improvement of the developed academic products | ULSA, all academic partners | 2018-08-15 | 365 | 2019-08-14 | 0% | 0 | 2018-08-14 | not started
3.6 | Preparation of approval of new and adapted educational products into existing curricula | ULSA, all academic partners | 2018-12-15 | 243 | 2019-08-14 | 0% | 0 | 2018-12-14 | not started
4 | Continuing professional development (CPD) | BOKU | 2017-05-15 | 822 | 2019-08-14 | 0% | 0 | 2017-05-14 | not started
4.1 | Detailed definition of CPD educational products to be adapted and developed | BOKU, all other partners | 2017-05-15 | 153 | 2017-10-14 | 0% | 0 | 2017-05-14 | not started
4.2 | Adaptation of existing educational products for CPD | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 0% | 0 | 2017-05-14 | not started
4.3 | Development of NEW CPD educational products | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 0% | 0 | 2017-05-14 | not started
4.4 | Train-the-trainer on new and adapted CPD educational products | BOKU, all other partners | 2018-06-15 | 426 | 2019-08-14 | 0% | 0 | 2018-06-14 | not started
4.5 | Piloting and improvement of the developed CPD products | BOKU, all other partners | 2018-08-15 | 365 | 2019-08-14 | 0% | 0 | 2018-08-14 | not started
4.6 | Certification of new and adapted educational CPD products | UFRJ, all other partners | 2018-12-15 | 243 | 2019-08-14 | 0% | 0 | 2018-12-14 | not started
5 | Teaching tools and techniques | TUON | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1 | Selection, development and adaptation of state of the art of modern teaching tools and methods | TUON, all University partners | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1.1 | Implementation of e-learning | TUON, all other partners | 2017-05-15 | 335 | 2018-04-14 | 0% | 0 | 2017-05-14 | not started
5.1.2 | Development of a “Digital library” | TUON | 2017-05-15 | 883 | 2019-10-14 | 0% | 0 | 2017-05-14 | not started
5.1.3 | Trainings related to entrepreneurial skills | BOKU, all other partners | 2017-08-15 | 426 | 2018-10-14 | 0% | 0 | 2017-08-14 | not started
5.1.4 | Implementation of shared trainings work stations | UFRJ, all other partners | 2017-08-15 | 426 | 2018-10-14 | 0% | 0 | 2017-08-14 | not started
5.2 | Piloting and improvement of new tools | TUON, all partners | 2018-11-15 | 120 | 2019-03-14 | 0% | 0 | 2018-11-14 | not started
5.3 | Prepare Integration of new tools into the University structures as well as at Companies site and in the collaboration centre | UNESP, all other Partners from Brazil and Nicaragua | 2017-11-15 | 577 | 2019-06-14 | 0% | 0 | 2017-11-14 | not started
6 | Project Monitoring and Quality Assurance | TUHH | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
6.1 | Development of a Quality Plan/Guidelines and exchange of best practise | TUHH, all partners | 2016-10-15 | 182 | 2017-04-14 | 0% | 0 | 2016-10-14 | not started
6.2 | Implementation of continuous Quality monitoring | TUHH, all WP Leaders with support of WP contributors | 2017-01-15 | 1003 | 2019-10-14 | 0% | 0 | 2017-01-14 | not started
6.3 | Coordination of documentation of best practise and lessons learned from trainings development and integration | TUHH, all WP Leaders | 2017-04-15 | 913 | 2019-10-14 | 0% | 0 | 2017-04-14 | not started
7 | Project Dissemination and Exploitation | UNESP | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.1 | Development of a detailed Dissemination strategy | UNESP, all other partners | 2016-10-15 | 92 | 2017-01-14 | 0% | 0 | 2016-10-14 | not started
7.2 | Development of website and dissemination material | UNESP, all partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.3 | Ongoing engagement of all stakeholder groups and support of consortium partners | UNESP, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
7.4 | IPR management and Exploitation | BOKU, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 0% | 0 | 2016-10-14 | not started
8 | Project Management | BOKU | 2016-10-15 | 1095 | 2019-10-14 | #DIV/0! | #DIV/0! | #DIV/0! | not started
Formulas:
CalcDate = [Start]+[CalcDone]-1

## auf PM final
Latin American-European network on waste electrical and electronic equipment research, development and analyses" (LaWEEEda)
| Project Coordination: | BOKU |  | Version: | 1.0
| Project start | 2016-10-15 |  | Status: | Beginning
| Today | 2017-05-09
[7 empty] | 15.10. | 15.11. | 15.12. | 15.01. | 15.02. | 15.03. | 15.04. | 15.05. | 15.06. | 15.07 | 15.08. | 15.09. | 15.10. | 15.11. | 15.12. | 15.01. | 15.02. | 15.03. | 15.04. | 15.05. | 15.06. | 15.07 | 15.08. | 15.09. | 15.10. | 15.11. | 15.12. | 15.01. | 15.02. | 15.03. | 15.04. | 15.05. | 15.06. | 15.07 | 15.08. | 15.09.
[7 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
WP | Task | Responsibility | Start | Duration [days] | End of WP | Duration | PM 1 | PM 2 | PM 3 | PM 4 | PM 5 | PM 6 | PM 7 | PM 8 | PM 9 | PM 10 | PM 11 | PM 12 | PM 13 | PM 14 | PM 15 | PM 16 | PM 17 | PM 18 | PM 19 | PM 20 | PM 21 | PM 22 | PM 23 | PM 24 | PM 25 | PM 26 | PM 27 | PM 28 | PM 29 | PM 30 | PM 31 | PM 32 | PM 33 | PM 34 | PM 35 | PM 36
0 | Projekt Coordination | BOKU | 2016-10-15 | 1095 | 2019-10-14 | 36.4667
1 | Creating the information basis | TUHH | 2016-10-15 | 212 | 2017-05-14 | 7.0333 | bar: 15.10. to 15.04.
1.1 | Compilation of a holistic inventory of existing teaching/training capacities and related gaps and needs | TUHH, all partners | 2016-10-15 | 151 | 2017-03-14 | 5 | 15.01.: D.1.1
1.2 | Compilation of established University-Enterprises collaboration approaches and best practise examples (at the participating organisation and in the area of e-waste management) | TUHH, partners | 2016-10-15 | 151 | 2017-03-14 | 5 | 15.01.: D.1.2
1.3 | Preparatory activities regarding specific national and regional, social, gender and ethical aspects respecting national and regional specialities | ULSA, all partners from partner countries | 2016-10-15 | 151 | 2017-03-14 | 5 | 15.04.: D.1.3
1.4 | Selection of modules, courses and educational products for academic education and CPD | TUHH, all partners | 2017-02-15 | 89 | 2017-05-14 | 2.9333 | 15.04.: D.1.4
1.5 | Organisation of preparatory workshops | ULSA | 2016-12-15 | 151 | 2017-05-14 | 5 | bar: 15.12. to 15.04.
2 | University-Enterprise Collaboration and Trainings centre | UFRJ | 2017-05-15 | 883 | 2019-10-14 | 29.4 | bar: 15.05. to 15.09.
2.1 | Planning and development of the LaWEEda University-Enterprise Business and Trainings centres and Network | UFRJ, all other partners | 2017-05-15 | 822 | 2019-08-14 | 27.3667 | 15.03.: D.2.1
2.2 / 2.3 | Develop roadmaps | UFRJ, all other partners | 2017-11-15 | 699 | 2019-10-14 | 23.2667 | 15.05.: D.2.2; 15.07: D.2.3
2.4 | Implementation of a web platform to support the centre | BOKU, UFRJ | 2017-11-15 | 638 | 2019-08-14 | 21.2333 | 15.06.: D.2.4
2.5 | Businessplan development | UFRJ, all other partners | 2018-04-15 | 487 | 2019-08-14 | 16.2 | 15.06.: D.2.5
3 | Academic Education | ULSA | 2017-05-15 | 822 | 2019-08-14 | 27.3667 | bar: 15.05. to 15.07
3.1 | Detailed definition of academic educational products to be adapted and developed | BOKU, all academic partners, input from non-academic partners | 2017-05-15 | 153 | 2017-10-14 | 5.0667 | 15.09.: D.3.1
3.2 | Adaptation of educational products for Academic Education | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 7.0333 | 15.05.: D.3.2.
3.3 | Development of NEW higher education products | ULSA, all academic partners, input from non-academic partners | 2017-11-15 | 212 | 2018-06-14 | 7.0333 | 15.05.: D.3.3
3.4 | Train-the-teacher on new and adapted higher education products | ULSA, all academic partners | 2018-06-15 | 426 | 2019-08-14 | 14.1667 | 15.07: D.3.4
3.5 | Piloting and improvement of the developed academic products | ULSA, all academic partners | 2018-08-15 | 365 | 2019-08-14 | 12.1333 | bar: 15.08. to 15.07
3.6 | Preparation of approval of new and adapted educational products into existing curricula | ULSA, all academic partners | 2018-12-15 | 243 | 2019-08-14 | 8.0667 | bar: 15.12. to 15.07
4 | Continuing professional development (CPD) | BOKU | 2017-05-15 | 822 | 2019-08-14 | 27.3667 | bar: 15.05. to 15.07
4.1 | Detailed definition of CPD educational products to be adapted and developed | BOKU, all other partners | 2017-05-15 | 153 | 2017-10-14 | 5.0667 | 15.09.: D.4.1
4.2 | Adaptation of existing educational products for CPD | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 13.1667 | 15.05.: D.4.2
4.3 | Development of NEW CPD educational products | BOKU, all other partners | 2017-05-15 | 396 | 2018-06-14 | 13.1667 | 15.05.: D.4.3
4.4 | Train-the-trainer on new and adapted CPD educational products | BOKU, all other partners | 2018-06-15 | 426 | 2019-08-14 | 14.1667 | 15.07: D.4.4
4.5 | Piloting and improvement of the developed CPD products | BOKU, all other partners | 2018-08-15 | 365 | 2019-08-14 | 12.1333 | bar: 15.08. to 15.07
4.6 | Certification of new and adapted educational CPD products | UFRJ, all other partners | 2018-12-15 | 243 | 2019-08-14 | 8.0667 | bar: 15.12. to 15.07
5 | Teaching tools and techniques | TUON | 2017-05-15 | 883 | 2019-10-14 | 29.4 | bar: 15.05. to 15.09.
5.1 | Selection, development and adaptation of state of the art of modern teaching tools and methods | TUON, all University partners | 2017-05-15 | 883 | 2019-10-14 | 29.4 | bar: 15.05. to 15.09.
5.1.1 | Implementation of e-learning | TUON, all other partners | 2017-05-15 | 335 | 2018-04-14 | 11.1333 | 15.03.: D.5.1
5.1.2 | Development of a “Digital library” | TUON | 2017-05-15 | 883 | 2019-10-14 | 29.4 | 15.03.: D.5.2
5.1.3 | Trainings related to entrepreneurial skills | BOKU, all other partners | 2017-08-15 | 426 | 2018-10-14 | 14.1667 | 15.03.: D.5.3
5.1.4 | Implementation of shared trainings work stations | UFRJ, all other partners | 2017-08-15 | 426 | 2018-10-14 | 14.1667 | bar: 15.08. to 15.09.
5.2 | Piloting and improvement of new tools | TUON, all partners | 2018-11-15 | 120 | 2019-03-14 | 3.9667 | bar: 15.11. to 15.02.
5.3 | Prepare Integration of new tools into the University structures as well as at Companies site and in the collaboration centre | UNESP, all other Partners from Brazil and Nicaragua | 2017-11-15 | 577 | 2019-06-14 | 19.2 | 15.08.: D.5.4
6 | Project Monitoring and Quality Assurance | TUHH | 2016-10-15 | 1095 | 2019-10-14 | 36.4667
6.1 | Development of a Quality Plan/Guidelines and exchange of best practise | TUHH, all partners | 2016-10-15 | 182 | 2017-04-14 | 6.0333 | 15.03.: D.6.1
6.2 | Implementation of continuous Quality monitoring | TUHH, all WP Leaders with support of WP contributors | 2017-01-15 | 1003 | 2019-10-14 | 33.4 | 15.09.: D.6.2; 15.03.: D.6.3; 15.09.: D.6.4; 15.03.: D.6.5; 15.09.: D.6.6
6.3 | Coordination of documentation of best practice and lessons learned from trainings development and integration | TUHH, all WP Leaders | 2017-04-15 | 913 | 2019-10-14 | 30.4 | bar: 15.04. to 15.09.
7 | Project Dissemination and Exploitation | UNESP | 2016-10-15 | 1095 | 2019-10-14 | 36.4667
7.1 | Development of a detailed Dissemination strategy | UNESP, all other partners | 2016-10-15 | 92 | 2017-01-14 | 3.0333 | 15.12.: D.7.1
7.2 | Development of website and dissemination material | UNESP, all partners | 2016-10-15 | 1095 | 2019-10-14 | 36.4667 | 15.12.: D.7.2; 15.03.: D.7.3
7.3 | Ongoing engagement of all stakeholder groups and support of consortium partners | UNESP, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 36.4667
7.4 | IPR management and Exploitation | BOKU, all other partners | 2016-10-15 | 1095 | 2019-10-14 | 36.4667 | 15.07: D.7.4; 15.09.: D.7.5; 15.10.: D.7.6
8 | Project Management | BOKU | 2016-10-15 | 1095 | 2019-10-14 | 36.4667 | 15.12.: D.8.1; 15.01.: D.8.2; 15.09.: D.8.4; 15.03.: D.8.3; 15.09.: D.8.5; 15.09.: D.8.6
D.8.7.